## User_Stories
User Stories: Equipment / Tool Request Approval
Written against the future-state process map. US-09 (explicit rejection path) was added after UAT test planning surfaced a gap in the original design; see UAT_Test_Plan tab, TC-12.
ID | Epic | User Story | Acceptance Criteria | Priority (MoSCoW) | Story Points
US-01 | Self-service intake | As an employee, I want to submit an equipment request through a self-service portal with structured fields (item, cost center, justification) so that my request is captured completely without email back-and-forth. | Given I am logged into the portal, when I submit without a required field, then submission is blocked and the missing field is highlighted. Given all fields are complete, when I submit, then a ticket is created with a unique ID and I receive confirmation. | Must | 5
US-02 | Policy validation | As the system, I want to validate each request against policy and budget rules automatically so that invalid or unbudgeted requests are flagged before reaching an approver. | Given a submitted request, when the cost exceeds the department's remaining budget, then it is flagged for manager and finance review. Given the item matches an approved catalog entry within budget, then it proceeds to routing without manual policy review. | Must | 8
US-03 | Auto-routing | As the system, I want to auto-route validated requests to the correct approver using a cost-center matrix so that requests reach the right person without manual forwarding. | Given a validated request, when the cost center is identified, then the request routes to that cost center's designated approver within 1 minute of submission. | Must | 5
US-04 | SLA-timed approval | As an approver, I want a defined SLA window to approve or reject requests so that requests don't stall indefinitely. | Given a routed request, when 24 hours pass with no action, then the requester and approver receive a reminder. Given 48 hours pass with no action, then the request auto-escalates. | Must | 3
US-05 | Auto-escalation | As the system, I want to auto-escalate unactioned requests to the next-level approver so that delays resolve without manual follow-up. | Given a request has passed its SLA without action, when escalation triggers, then the next-level approver is notified and the original approver is copied. | Should | 3
US-06 | Auto-generated fulfillment ticket | As IT/Procurement, I want an auto-generated, pre-populated fulfillment ticket after approval so that I don't manually re-enter request details. | Given a request is approved, when the fulfillment ticket is created, then it includes item, quantity, cost center, requester, and delivery location without manual entry. | Must | 5
US-07 | Status visibility | As an employee, I want to see the real-time status of my request so that I don't need to email IT to check progress. | Given I have a submitted request, when I check the portal, then I see the current stage (submitted, approved, fulfilling, delivered) and an expected completion date. | Should | 3
US-08 | Auto-close | As IT/Procurement, I want the ticket to auto-close once equipment is marked delivered so that closed tickets don't need manual cleanup. | Given fulfillment is marked complete, when IT confirms delivery, then the ticket auto-closes and the requester receives a confirmation notification. | Must | 2
US-09 | Explicit rejection path | As an approver, I want to reject a request with a stated reason so that the requester understands why it did not proceed, instead of the request simply stalling. | Given a routed request, when the approver selects Reject and enters a reason, then the requester is notified with that reason and the ticket closes as Rejected, not left open or auto-escalated. | Must | 2
US-10 | Bottleneck dashboard | As a Digital Workplace analyst, I want a dashboard of average cycle time and approval delay by cost center so that I can identify bottlenecks after launch. | Given tickets are being processed, when I open the dashboard, then I see average cycle time trending by week and by approver. | Could | 8
Total story points: 44. MoSCoW: 7 Must, 2 Should, 1 Could.

## UAT_Test_Plan
UAT Test Plan: Equipment / Tool Request Approval
Status column left blank (Not run) for use during actual UAT execution.
Test ID | Linked Story | Scenario | Steps | Expected Result | Priority | Status
TC-01 | US-01 | Submit a complete request | Fill all required fields, click Submit. | Ticket created with unique ID; confirmation shown. | High | Not run
TC-02 | US-01 | Submit with a missing field | Leave cost center blank, click Submit. | Submission blocked; cost center field highlighted. | High | Not run
TC-03 | US-02 | Request exceeds budget | Submit a request above the department's remaining budget. | Request flagged for manager and finance review. | High | Not run
TC-04 | US-02 | Request within budget, catalog item | Submit a standard catalog item within budget. | Request auto-proceeds to routing without manual review. | Medium | Not run
TC-05 | US-03 | Routing accuracy | Submit requests from 3 different cost centers. | Each routes to that cost center's correct designated approver. | High | Not run
TC-06 | US-04 | Approve within SLA | Approver actions the request within 24 hours. | Request proceeds to IT/procurement notification. | High | Not run
TC-07 | US-04 | No action at 24 hours | Leave a routed request unactioned for 24 hours. | Reminder notification sent to requester and approver. | Medium | Not run
TC-08 | US-05 | No action at 48 hours | Leave a routed request unactioned for 48 hours. | Request auto-escalates; next-level approver notified, original approver copied. | High | Not run
TC-09 | US-06 | Fulfillment ticket auto-population | Approve a request and inspect the generated IT/procurement ticket. | Ticket includes item, quantity, cost center, requester, and delivery location with no manual entry needed. | High | Not run
TC-10 | US-07 | Status check | Requester opens the portal after submitting. | Current stage and expected completion date are visible. | Medium | Not run
TC-11 | US-08 | Auto-close on delivery | IT marks the item delivered. | Ticket auto-closes; requester receives confirmation. | Medium | Not run
TC-12 | US-09 | Explicit rejection | Approver selects Reject and enters a reason. | Requester notified with the reason; ticket closes as Rejected, does not escalate. | High | Not run
TC-13 | Regression | Duplicate submission | Submit the same request twice within 1 minute. | System either blocks the duplicate or flags it for review, does not silently create two fulfillment tickets. | Medium | Not run
TC-13 (duplicate submission) has no linked user story: found during test-case writing, not covered by any story above. Flagged as a backlog gap, not silently fixed by adding a story after the fact.

## Risk_Dependency_Tracker
Risk & Dependency Tracker: Pilot (Equipment/Tool Request + Onboarding)
Score = Likelihood x Impact. Sort descending to prioritize mitigation effort.
ID | Type | Description | Likelihood (1-5) | Impact (1-5) | Score | Owner | Mitigation | Status
R-01 | Risk | ServiceNow platform team bandwidth conflicts with other roadmap priorities. | 4 | 4 | 16 | Digital Workplace Lead | Secure dedicated sprint capacity commitment before kickoff. | Open
R-02 | Risk | Cost-center and budget data not cleanly available for auto-validation rules. | 3 | 4 | 12 | Finance Systems Liaison | Run a data audit in Sprint 0 before build starts. | Open
R-03 | Risk | Low adoption if employees default back to email or verbal requests out of habit. | 3 | 3 | 9 | Change Management Lead | Disable the old intake channel post-pilot; redirect all requests to the portal. | Open
R-04 | Risk | Approver escalation matrix incomplete for edge-case cost centers (e.g. shared or fab-floor budgets). | 3 | 3 | 9 | Requirements Owner (BA) | Validate the full matrix against every cost center before UAT begins. | Open
R-05 | Dependency | Requires a ServiceNow admin change window, shared with the Onboarding build on the same platform. | 3 | 4 | 12 | ServiceNow Platform Team | Sequence both builds in the same sprint to share configuration effort (see bundled-cost note in ROI_Model). | Open
R-06 | Dependency | IT/Procurement must confirm they can consume auto-generated tickets in their existing queue without a separate manual re-entry step. | 2 | 4 | 8 | IT/Procurement Lead | Confirm ticket field mapping with IT/Procurement before Sprint 2 build. | Open
R-07 | Risk | No explicit rejection path existed in the original process design; found during UAT test planning (TC-12), not before. | 5 | 3 | 15 | Requirements Owner (BA) | US-09 added to backlog to close the gap before build starts. | Mitigated in backlog
R-07 is a live example of this project's own process: a gap the model didn't catch until test planning, caught and closed before build rather than during production.

## Change_Management_Plan
Change Management & Adoption Plan
Pilot: Equipment/Tool Request Approval, one cost center first
Phase | Timeline | Actions | Owner | Success Metric
1. Pilot | Weeks 1-2 | Launch with one cost center. Assign a change champion in that team. Capture baseline metrics (current avg cycle time, ticket volume) before go-live for comparison. | Change Management Lead | Pilot cost center live; baseline metrics documented.
2. Feedback & Iterate | Weeks 3-4 | Collect pilot feedback via short survey and change-champion check-ins. Fix top issues. Refine the approver routing matrix based on real submissions. | BA / Requirements Owner | Top 3 pilot issues resolved before expansion.
3. Expand | Weeks 5-8 | Roll out to remaining cost centers in waves, not all at once. Disable the old email/verbal intake channel once each wave is live. | Digital Workplace Lead | All cost centers migrated; old channel usage at zero.
4. Stabilize | Weeks 9-12 | Monitor adoption and cycle-time KPIs weekly. Hold a final review. Decommission any legacy tracking spreadsheets. | Digital Workplace Lead | 80%+ requests via portal; cycle time meets the under-3-day target from the process map.
Communication & Training
- Kickoff announcement (email + Teams) before pilot launch, explaining what's changing and why.
- One-page quick-reference guide for the new portal, distributed with the kickoff announcement.
- Office hours during pilot week 1 for live questions.
- One change champion per department: not the BA, a peer who models the new process and answers informal questions.
Multi-Site Rollout Considerations
Micron operates fabs and sites across multiple US locations (Boise ID, Manassas VA, Syracuse NY expansion) and internationally (Hiroshima Japan, Taiwan, Singapore, Sanand India). A single-timezone, single-champion rollout plan does not scale to that footprint. Adjustments for actual rollout:
- Change champion assigned per site, not per department alone; a Boise-based champion cannot cover a Syracuse shift's informal questions in real time.
- Office hours (Phase 1) held at times that cover at least two major timezones, or recorded and made async-available for fab shift workers who are not at a desk during standard office hours.
- Wave sequencing (Phase 3) treats each site as its own wave, not a single global cutover, since local ServiceNow configuration and cost-center mappings differ by site.
Adoption Metrics (defined before rollout, not after)
- % of requests submitted via portal vs. old channel
- Average end-to-end cycle time (target: under 3 business days, per process map)
- Approver SLA compliance rate
- Requester satisfaction, quick pulse survey after each wave

## Sprint_Backlog
Sprint Backlog: Equipment / Tool Request Approval
3 build sprints + Sprint 0 discovery. Onboarding epic runs in parallel in Sprint 1, sharing ServiceNow admin time (see ROI_Model bundled-cost scenario).
Sprint | Item | Description | Points | Status
Sprint 0 (1 wk) | Discovery | Cost-center data audit (R-02). Approver matrix validation (R-04). Existing ServiceNow catalog review, shared with Onboarding build (R-05). | - | Planned
Sprint 1 (2 wks) | US-01 | Self-service intake form with structured fields and validation. | 5 | Planned
Sprint 1 (2 wks) | US-02 | Policy and budget validation rules. | 8 | Planned
Sprint 1 (2 wks) | US-03 | Auto-routing via cost-center matrix. | 5 | Planned
Sprint 1 (2 wks) | Onboarding epic (parallel) | Onboarding provisioning workflow build, same ServiceNow sprint per bundled-cost scenario. | - | Planned
Sprint 2 (2 wks) | US-04 | SLA-timed approve/reject with reminders. | 3 | Planned
Sprint 2 (2 wks) | US-05 | Auto-escalation to next-level approver. | 3 | Planned
Sprint 2 (2 wks) | US-06 | Auto-generated, pre-populated IT/procurement ticket. | 5 | Planned
Sprint 2 (2 wks) | US-09 | Explicit rejection path with stated reason. | 2 | Planned
Sprint 3 (2 wks) | US-07 | Requester-facing status visibility. | 3 | Planned
Sprint 3 (2 wks) | US-08 | Auto-close on delivery confirmation. | 2 | Planned
Sprint 3 (2 wks) | UAT execution | Run TC-01 through TC-13 (UAT_Test_Plan tab). | - | Planned
Sprint 3 (2 wks) | Pilot launch prep | Change management Phase 1 actions (Change_Management_Plan tab). | - | Planned
Backlog (not scheduled) | US-10 | Bottleneck dashboard by cost center and approver. | 8 | Backlog
Backlog (concept only, not scoped) | US-11 (stretch) | Predictive request initiation: system flags likely equipment needs from usage/lifecycle data and drafts a request for the employee to confirm, instead of waiting for a manual submission. This would be genuinely agentic (autonomous, adaptive), not rule-based like US-01 through US-09. Not scoped, not pointed, not part of this MVP. See README, 'Beyond This MVP.' | - | Concept
Scheduled points: 36 (US-01 through US-09, excluding backlog item US-10).

## Functional_Spec_US-02
Functional Specification: Policy & Budget Validation (US-02)
The one story in the backlog with real business-rule complexity. User stories say what the system should do; this says exactly how.
1. Overview
When an employee submits an equipment/tool request via the self-service portal, the system must automatically validate it against two rule sets, budget availability and catalog/policy compliance, before routing to an approver. This replaces the manual policy check currently performed informally by the approving manager.
2. Trigger
Request submission event (US-01 complete) fires the validation service.
3. Inputs
- Requested item (catalog SKU or free-text description)
- Requested cost (catalog price or manual estimate)
- Requester's cost center and employee ID
- Fiscal year / quarter (for budget period lookup)
4. Business Rules
Rule | Condition | Result
BR-1 | Item matches approved catalog SKU AND cost <= department's remaining quarterly budget |  | Auto-proceed to routing (US-03), no manual review
BR-2 | Cost exceeds department's remaining quarterly budget |  | Status = Budget Review Required; routes to requester's manager AND Finance Systems Liaison
BR-3 | Item does not match an approved catalog SKU (non-standard request) |  | Status = Policy Review Required; routes to manager with policy-exception note
BR-4 | Both BR-2 and BR-3 conditions true |  | Status = Combined Review Required; routes to manager, Finance Systems Liaison, and a Digital Workplace analyst
BR-5 | Budget remaining calculation |  | Approved quarterly budget minus sum of already-approved requests this quarter, including pending Budget Review Required requests not yet rejected
5. Outputs
- Request status field updated (Auto-Approved-Pending-Routing / Budget-Review-Required / Policy-Review-Required / Combined-Review-Required)
- Audit log entry: rule(s) triggered, timestamp, evaluated budget figures
- Notification to requester confirming validation outcome (not full approval)
6. Exception Handling
- Budget data unavailable (new cost center, sync failure): request held in Data Pending status, routed to Finance Systems Liaison with a 24-hour SLA (ties to R-02 in the risk tracker).
- Catalog data stale (item recently deprecated): flagged for manual catalog review, not silently blocked.
7. Data Dependencies
- Real-time or near-real-time department budget balance feed (owned by Finance Systems)
- Current approved-catalog list (owned by Procurement / IT Asset Management)
- Cost-center hierarchy mapping (owned by HR / Finance)
8. Non-Functional Requirements
- Validation completes within 60 seconds of submission (supports the under-1-minute routing target in US-03's acceptance criteria).
- All rule evaluations logged for audit purposes; real spend is involved, which makes this a financial control, not just a workflow step.
9. Open Questions (flagged, not resolved)
- Is remaining budget checked at cost-center level or program level? Assumed cost-center level here; needs confirmation with the Finance Systems Liaison before build (ties to R-02).
- Does a rejected Budget Review Required request release its reserved budget immediately, or is there a hold period? Not yet defined.

## AI_Assisted_UAT_Notes
Where AI Actually Helped (and Where It Didn't)
Writing test cases from user stories is repetitive, first-draft work. That's a real fit for an LLM. This shows the exact prompt used, what came back, and what a human still had to catch.
Prompt used
"Given this user story and its acceptance criteria, draft 2-3 UAT test cases. Format: Test ID, Scenario, Steps, Expected Result. Story: US-09, As an approver, I want to reject a request with a stated reason so that the requester understands why it did not proceed, instead of the request simply stalling. Acceptance criteria: Given a routed request, when the approver selects Reject and enters a reason, then the requester is notified with that reason and the ticket closes as Rejected, not left open or auto-escalated."
Raw AI-drafted output (unedited)
Test ID | Scenario | Steps | Expected Result
TC-A | Reject a request | Approver opens the request and selects Reject. | The request is rejected.
TC-B | Reject without a reason | Approver selects Reject and leaves the reason field blank. | System prompts the approver to enter a reason before proceeding.
What a human had to catch
Missed the actual point of the story
TC-A's "the request is rejected" is generic. It never tests the one behavior US-09 exists to guarantee: that a rejected ticket does not auto-escalate, which was the real gap (R-07) found during test planning. A generic AI-drafted test case can pass while missing the requirement it was supposed to verify.
Invented behavior not in the spec
TC-B assumes the system enforces a mandatory reason field with a blocking prompt. Nothing in the acceptance criteria says that. Keeping this test case would have shipped a requirement nobody actually wrote. It was dropped rather than kept "just in case."
What shipped instead
TC-12 in UAT_Test_Plan explicitly tests: "Requester notified with the reason; ticket closes as Rejected, does not escalate." That distinguishing detail came from re-reading the acceptance criteria against what R-07 was actually flagging, not from the AI draft.
Where this generalizes
LLM-drafted first passes are a real time-saver for volume, boilerplate test structure, and covering the obvious happy path. They are not a substitute for knowing which single test case actually matters for a given story, or for noticing when a draft has quietly invented a requirement. On this team, the useful pattern is: AI drafts, a person checks the draft against the actual risk it's supposed to catch, not just against the story text.